## How to use
LMS Progress Tracker
What this file does | Shows you, in one place, who is ahead, who is behind and who is stuck.
Step 1 | Open the 'Team' sheet. Type each person's real name in the yellow cells. Set the project start Monday (yellow cell).
Step 2 | Team members update ONLY these columns on the 'Tasks' sheet: Status (I), Blocked? (J), Actual hours (L), Review rounds (M), Notes (O).
Step 3 | Do not type in grey columns. They are formulas (Person, Due date, Overdue).
Step 4 | Look at the 'Summary' sheet every Wednesday and Friday. GREEN = fine, AMBER = talk to the person, RED = help now.
Blue text | Cells where you type. Black text = formulas. Yellow fill = settings you should check first.
Example row | Task LMS-203 ¦ Status: In review ¦ Blocked?: (empty) ¦ Actual hours: 9 ¦ Review rounds: 1 ¦ Notes: PR #14 waiting for lead
Health rule | RED if 3 or more overdue tasks or 2 or more blocked tasks. AMBER if 1-2 overdue or 1 blocked. Otherwise GREEN.
Overdue rule | A task is OVERDUE when it is not Done and today is after the last day (Friday) of its sprint.

## Summary
Progress summary
Today: | 2026-09-30
By person
Tag | Person | Tasks | Done | In review/testing | In progress | Not started | Blocked | Overdue | % tasks done | Estimated h | Done h (estimate) | Actual h (done tasks) | Avg review rounds | Health
PM | Lead (you) | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0% | 9 | 0 | 0 | 0 | GREEN
BE-1 | Name 1 | 15 | 6 | 0 | 0 | 9 | 0 | 0 | 40% | 62 | 17 | 0 | 0 | GREEN
BE-2 | Name 2 | 12 | 2 | 0 | 0 | 10 | 0 | 0 | 16.67% | 60 | 6 | 0 | 0 | GREEN
BE-3 | Name 3 | 16 | 7 | 0 | 0 | 9 | 0 | 0 | 43.75% | 60 | 18 | 0 | 0 | GREEN
FE | Name 4 | 11 | 0 | 0 | 0 | 11 | 0 | 0 | 0% | 60 | 0 | 0 | 0 | GREEN
QA | Name 5 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | 0% | 48 | 0 | 0 | 0 | GREEN
Total |  | 64 | 15 | 0 | 0 | 49 | 0 | 0 | 23.44% | 299 | 41 | 0
By sprint
Sprint |  | Tasks | Done | In review/testing | In progress | Not started | Blocked | Overdue | % tasks done | Estimated h | Done h (estimate) | Ends
Sprint 0 - Setup |  | 8 | 4 | 0 | 0 | 4 | 0 | 0 | 50% | 21 | 9 | 2026-10-09
Sprint 1 - Accounts and Roles |  | 11 | 5 | 0 | 0 | 6 | 0 | 0 | 45.45% | 50 | 16 | 2026-10-23
Sprint 2 - Courses, Units and Home Page |  | 11 | 2 | 0 | 0 | 9 | 0 | 0 | 18.18% | 52 | 5 | 2026-11-06
Sprint 3 - Applications and Enrollment |  | 9 | 2 | 0 | 0 | 7 | 0 | 0 | 22.22% | 37 | 4 | 2026-11-13
Sprint 4 - Assessments and Feedback |  | 8 | 1 | 0 | 0 | 7 | 0 | 0 | 12.5% | 42 | 4 | 2026-11-27
Sprint 5 - Attendance |  | 8 | 1 | 0 | 0 | 7 | 0 | 0 | 12.5% | 39 | 3 | 2026-12-04
Sprint 6 - Dashboards, Polish and Release |  | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0% | 58 | 0 | 2026-12-18
Note: 'Done h (estimate)' adds the estimated hours of finished tasks. Compare it with 'Actual h' to see who under- or over-estimates.

## Team
Team and settings
Project start (a Monday) | 2026-10-05 | Assumption: kick-off on the first Monday after 29 Sep 2026. Change if your start date is different.
Tag | Person (type name) | Main job | Main apps they own
PM | Lead (you) | Plans, reviews every pull request, removes blockers, runs demos | All (reviewer)
BE-1 | Name 1 | Foundation and security: user model, roles, mixins, sensitive logic | accounts, attendance
BE-2 | Name 2 | Courses and applications, admin pages, deployment | courses, enrollments
BE-3 | Name 3 | Login pages, marks, reports, data rules | assessments, core
FE | Name 4 | Templates, Bootstrap, how every page looks and feels | templates/, static/
QA | Name 5 | Tests, bug reports, user acceptance testing | tests/
Sprint calendar
Sprint | Start week (0 = week 1) | End week (weeks from start) | Starts (Monday) | Ends (Friday)
Sprint 0 - Setup | 0 | 1 | 2026-10-05 | 2026-10-09
Sprint 1 - Accounts and Roles | 1 | 3 | 2026-10-12 | 2026-10-23
Sprint 2 - Courses, Units and Home Page | 3 | 5 | 2026-10-26 | 2026-11-06
Sprint 3 - Applications and Enrollment | 5 | 6 | 2026-11-09 | 2026-11-13
Sprint 4 - Assessments and Feedback | 6 | 8 | 2026-11-16 | 2026-11-27
Sprint 5 - Attendance | 8 | 9 | 2026-11-30 | 2026-12-04
Sprint 6 - Dashboards, Polish and Release | 9 | 11 | 2026-12-07 | 2026-12-18
Formulas:
Main apps they own = B2+7*[Person (type name)]
Ends (Friday) = B2+7*[Main job]-3

## Tasks
ID | Task | Owner tag | Person | Sprint | Estimate (h) | Depends on | Priority | Status | Blocked? | Due (sprint end) | Actual hours | Review rounds | Overdue? | Notes
LMS-001 | Create GitHub repo, branch protection (main/develop), .gitignore, README | PM | Lead (you) | Sprint 0 - Setup | 1 |  | High | Not started |  | 2026-10-09
LMS-002 | Create Django project 'config' with split settings (base/dev/prod), django-environ, .env.example | BE-1 | Name 1 | Sprint 0 - Setup | 3 | LMS-001 | High | Done |  | 2026-10-09 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-003 | Set up PostgreSQL (local or docker-compose) and connect Django to it | BE-3 | Name 3 | Sprint 0 - Setup | 2 | LMS-002 | High | Done |  | 2026-10-09 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-004 | Create the 6 apps (core, accounts, courses, enrollments, assessments, attendance) and register them | BE-1 | Name 1 | Sprint 0 - Setup | 1 | LMS-002 | High | Done |  | 2026-10-09 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-005 | Base template: Bootstrap 5, navbar that changes per role, messages and pagination partials | FE | Name 4 | Sprint 0 - Setup | 4 | LMS-004 | High | Not started |  | 2026-10-09 |  |  |  | Basic version in the starter repo - finish it
LMS-006 | Add ruff/black, pre-commit and a GitHub Actions workflow that runs tests on every PR | BE-2 | Name 2 | Sprint 0 - Setup | 3 | LMS-001 | Medium | Done |  | 2026-10-09 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-007 | Create Slack channels, connect GitHub app, build the standup workflow and task board (see Slack section) | PM | Lead (you) | Sprint 0 - Setup | 2 |  | High | Not started |  | 2026-10-09
LMS-008 | Set up pytest + factory-boy and write the test-case checklist for workflows A to E | QA | Name 5 | Sprint 0 - Setup | 5 | LMS-004 | Medium | Not started |  | 2026-10-09 |  |  |  | Basic version in the starter repo - finish it
LMS-101 | Custom User model (role, phone, photo) - MUST be done before the first migrate | BE-1 | Name 1 | Sprint 1 - Accounts and Roles | 3 | LMS-004 | High | Done |  | 2026-10-23 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-102 | FacilitatorProfile and StudentProfile models + signal that creates the profile automatically | BE-1 | Name 1 | Sprint 1 - Accounts and Roles | 3 | LMS-101 | High | Done |  | 2026-10-23 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-103 | Student registration, login, logout and password reset (views + templates) | BE-3 | Name 3 | Sprint 1 - Accounts and Roles | 6 | LMS-101 | High | Not started |  | 2026-10-23 |  |  |  | Basic version in the starter repo - finish it
LMS-104 | Access-control mixins: RoleRequiredMixin, CourseManagerRequiredMixin | BE-1 | Name 1 | Sprint 1 - Accounts and Roles | 4 | LMS-102 | High | Done |  | 2026-10-23 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-105 | Admin user management: list, create facilitator, edit, activate/deactivate | BE-2 | Name 2 | Sprint 1 - Accounts and Roles | 6 | LMS-104 | High | Not started |  | 2026-10-23
LMS-106 | Admin facilitator list with grant / revoke 'can_manage_courses' button | BE-2 | Name 2 | Sprint 1 - Accounts and Roles | 4 | LMS-105 | High | Not started |  | 2026-10-23
LMS-107 | Profile view and edit pages for all roles | FE | Name 4 | Sprint 1 - Accounts and Roles | 4 | LMS-103 | Medium | Not started |  | 2026-10-23
LMS-108 | Dashboard redirect by role + three placeholder dashboards | BE-3 | Name 3 | Sprint 1 - Accounts and Roles | 3 | LMS-104 | Medium | Done |  | 2026-10-23 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-109 | Write tests: registration, login, role mixins, grant/revoke right | QA | Name 5 | Sprint 1 - Accounts and Roles | 6 | LMS-106 | High | Not started |  | 2026-10-23
LMS-110 | Management command create_demo_data (admin, facilitators, students, courses) | BE-3 | Name 3 | Sprint 1 - Accounts and Roles | 3 | LMS-102 | Low | Done |  | 2026-10-23 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-111 | Static HTML prototypes (home, course detail, dashboards) so pages are designed before the views exist | FE | Name 4 | Sprint 1 - Accounts and Roles | 8 | LMS-005 | Medium | Not started |  | 2026-10-23
LMS-201 | Course model, admin registration and migrations | BE-2 | Name 2 | Sprint 2 - Courses, Units and Home Page | 3 | LMS-104 | High | Done |  | 2026-11-06 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-202 | Unit model with facilitator FK and ordering | BE-3 | Name 3 | Sprint 2 - Courses, Units and Home Page | 2 | LMS-201 | High | Done |  | 2026-11-06 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-203 | Course create / update / delete views with ownership checks | BE-2 | Name 2 | Sprint 2 - Courses, Units and Home Page | 8 | LMS-201 | High | Not started |  | 2026-11-06
LMS-204 | Course form validation (dates, capacity) and image upload | BE-3 | Name 3 | Sprint 2 - Courses, Units and Home Page | 3 | LMS-203 | Medium | Not started |  | 2026-11-06
LMS-205 | Publish / close course action (status change) | BE-3 | Name 3 | Sprint 2 - Courses, Units and Home Page | 2 | LMS-203 | High | Not started |  | 2026-11-06
LMS-206 | Unit CRUD nested under a course + assign facilitator to unit | BE-1 | Name 1 | Sprint 2 - Courses, Units and Home Page | 6 | LMS-202 | High | Not started |  | 2026-11-06
LMS-207 | Home page: published course cards, search, filter, pagination | FE | Name 4 | Sprint 2 - Courses, Units and Home Page | 8 | LMS-205 | High | Not started |  | 2026-11-06 |  |  |  | Basic version in the starter repo - finish it
LMS-208 | Course detail page with unit list and smart 'Apply' button state | FE | Name 4 | Sprint 2 - Courses, Units and Home Page | 5 | LMS-205 | High | Not started |  | 2026-11-06 |  |  |  | Basic version in the starter repo - finish it
LMS-209 | 'Manage courses' table page for admin and course managers | FE | Name 4 | Sprint 2 - Courses, Units and Home Page | 4 | LMS-203 | Medium | Not started |  | 2026-11-06
LMS-210 | 'My units' page for facilitators (units I teach) | BE-1 | Name 1 | Sprint 2 - Courses, Units and Home Page | 3 | LMS-206 | Medium | Not started |  | 2026-11-06
LMS-211 | Tests: who can create / edit / delete, unpublished courses hidden from home | QA | Name 5 | Sprint 2 - Courses, Units and Home Page | 8 | LMS-207 | High | Not started |  | 2026-11-06
LMS-301 | Application model with unique (student, course) constraint | BE-3 | Name 3 | Sprint 3 - Applications and Enrollment | 2 | LMS-201 | High | Done |  | 2026-11-13 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-302 | Enrollment model | BE-3 | Name 3 | Sprint 3 - Applications and Enrollment | 2 | LMS-301 | High | Done |  | 2026-11-13 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-303 | Apply view + form; rules: window open, capacity, no duplicates | BE-2 | Name 2 | Sprint 3 - Applications and Enrollment | 5 | LMS-301 | High | Not started |  | 2026-11-13
LMS-304 | 'My applications' page with withdraw button | FE | Name 4 | Sprint 3 - Applications and Enrollment | 4 | LMS-303 | Medium | Not started |  | 2026-11-13
LMS-305 | Manage applications list with filters (status, course) | BE-3 | Name 3 | Sprint 3 - Applications and Enrollment | 5 | LMS-301 | High | Not started |  | 2026-11-13
LMS-306 | Approve / reject with note; service function creates Enrollment | BE-1 | Name 1 | Sprint 3 - Applications and Enrollment | 5 | LMS-302 | High | Not started |  | 2026-11-13
LMS-307 | Email on decision (console backend in dev, SMTP in prod) | BE-3 | Name 3 | Sprint 3 - Applications and Enrollment | 3 | LMS-306 | Low | Not started |  | 2026-11-13
LMS-308 | Student 'My courses' page + facilitator unit roster | FE | Name 4 | Sprint 3 - Applications and Enrollment | 5 | LMS-306 | Medium | Not started |  | 2026-11-13
LMS-309 | Tests: apply rules, approval flow, capacity edge cases | QA | Name 5 | Sprint 3 - Applications and Enrollment | 6 | LMS-306 | High | Not started |  | 2026-11-13
LMS-401 | Test, TestResult and Feedback models | BE-3 | Name 3 | Sprint 4 - Assessments and Feedback | 4 | LMS-302 | High | Done |  | 2026-11-27 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-402 | Test CRUD for the unit's facilitator | BE-2 | Name 2 | Sprint 4 - Assessments and Feedback | 6 | LMS-401 | High | Not started |  | 2026-11-27
LMS-403 | Bulk marks entry page (formset for all enrolled students) | BE-3 | Name 3 | Sprint 4 - Assessments and Feedback | 8 | LMS-402 | High | Not started |  | 2026-11-27
LMS-404 | Feedback create / update form linked to a result | BE-1 | Name 1 | Sprint 4 - Assessments and Feedback | 5 | LMS-403 | High | Not started |  | 2026-11-27
LMS-405 | Student results list and result detail with feedback | FE | Name 4 | Sprint 4 - Assessments and Feedback | 6 | LMS-404 | High | Not started |  | 2026-11-27
LMS-406 | Facilitator 'pending feedback' filter | BE-2 | Name 2 | Sprint 4 - Assessments and Feedback | 3 | LMS-404 | Medium | Not started |  | 2026-11-27
LMS-407 | In-app notification when feedback is added (optional) | BE-1 | Name 1 | Sprint 4 - Assessments and Feedback | 4 | LMS-404 | Low | Not started |  | 2026-11-27
LMS-408 | Tests: marks validation, feedback permissions, student privacy | QA | Name 5 | Sprint 4 - Assessments and Feedback | 6 | LMS-405 | High | Not started |  | 2026-11-27
LMS-501 | ClassSession and AttendanceRecord models | BE-1 | Name 1 | Sprint 5 - Attendance | 3 | LMS-302 | High | Done |  | 2026-12-04 |  |  |  | Provided in the starter repo - owner: read it, ask questions, improve via PR
LMS-502 | Session CRUD for the unit's facilitator | BE-1 | Name 1 | Sprint 5 - Attendance | 5 | LMS-501 | High | Not started |  | 2026-12-04
LMS-503 | Mark-attendance page (status per student, 'mark all present') | BE-1 | Name 1 | Sprint 5 - Attendance | 8 | LMS-502 | High | Not started |  | 2026-12-04
LMS-504 | Unit attendance report: % per student, highlight low attendance | BE-3 | Name 3 | Sprint 5 - Attendance | 6 | LMS-503 | High | Not started |  | 2026-12-04
LMS-505 | Export attendance to CSV / PDF | BE-3 | Name 3 | Sprint 5 - Attendance | 4 | LMS-504 | Medium | Not started |  | 2026-12-04
LMS-506 | Student 'My attendance' page | FE | Name 4 | Sprint 5 - Attendance | 4 | LMS-503 | Medium | Not started |  | 2026-12-04
LMS-507 | Admin attendance overview across all units | BE-2 | Name 2 | Sprint 5 - Attendance | 4 | LMS-504 | Low | Not started |  | 2026-12-04
LMS-508 | Tests: only unit facilitator can mark, no duplicate records | QA | Name 5 | Sprint 5 - Attendance | 5 | LMS-503 | High | Not started |  | 2026-12-04
LMS-601 | Admin dashboard: totals, pending applications, recent activity | BE-2 | Name 2 | Sprint 6 - Dashboards, Polish and Release | 6 | LMS-507 | High | Not started |  | 2026-12-18
LMS-602 | Facilitator dashboard: my units, upcoming sessions, pending feedback | BE-1 | Name 1 | Sprint 6 - Dashboards, Polish and Release | 5 | LMS-406 | High | Not started |  | 2026-12-18
LMS-603 | Student dashboard: my courses, next sessions, latest results, attendance % | BE-3 | Name 3 | Sprint 6 - Dashboards, Polish and Release | 5 | LMS-506 | High | Not started |  | 2026-12-18
LMS-604 | UI polish: responsive check, empty states, 403/404/500 pages | FE | Name 4 | Sprint 6 - Dashboards, Polish and Release | 8 | LMS-601 | Medium | Not started |  | 2026-12-18
LMS-605 | Performance pass: select_related / prefetch_related, indexes, pagination | BE-2 | Name 2 | Sprint 6 - Dashboards, Polish and Release | 4 | LMS-601 | Medium | Not started |  | 2026-12-18
LMS-606 | Security review using the checklist in this document | BE-1 | Name 1 | Sprint 6 - Dashboards, Polish and Release | 4 | LMS-601 | High | Not started |  | 2026-12-18
LMS-607 | Full regression + user acceptance testing with real users | QA | Name 5 | Sprint 6 - Dashboards, Polish and Release | 12 | LMS-604 | High | Not started |  | 2026-12-18
LMS-608 | Production settings, Gunicorn + Nginx / Whitenoise, env vars, DB backups | BE-2 | Name 2 | Sprint 6 - Dashboards, Polish and Release | 8 | LMS-606 | High | Not started |  | 2026-12-18
LMS-609 | Deploy, smoke test, hand-over documentation and training | PM | Lead (you) | Sprint 6 - Dashboards, Polish and Release | 6 | LMS-608 | High | Not started |  | 2026-12-18
Formulas:
Due (sprint end) = IFERROR(INDEX(Team!$E15:E21,MATCH([Sprint],Team!$A15:A21,0)),"")
Overdue? = IF(AND([Status]<>"Done",[Due (sprint end)]<>"",[Due (sprint end)]<TODAY()),"OVERDUE","")